## Slide 1: iDigBio Management and Progress
NSF Visit to iDigBio
May 7, 2014
David Jennings
iDigBio Project Manager

## Slide 2: Project Organization
Education & Outreach (MacFadden)
Serving the Research Community (Soltis)
Cyber-infrastructure (Fortes)
Digitization (Riccardi)
Administration (Page)

## Slide 3: Project Oversight
Executive Committee
Steering Committee
Internal Advisory Committee
External Advisory Board
NSF Program Officers
PIs
Project Manager
PIs
Project Manager
TCNs/PENs
Project Director
Senior Personnel
Project Director
Project Manager
Biodiversity Informatics Manager

## Slide 4: Strategic Plan
Define project mission, vision, & horizon
Define project organization & oversight
Establish high-level roadmaps for each domain
Perform Environmental Scan (SWOT Analysis)
Planning for Sustainability

## Slide 5: Environmental Scan
 | POSITIVE | NEGATIVE
INTERNAL | Strengths – iDigBio has… Successfully engaged with the collections community, particularly through workshops and working groups Developed a vast repository of resources information Optimized digitization protocols and workflows Actively reduced barriers to digitization Demonstrated strong leadership and management Developed partnerships and collaborations, including significant synergy with TCNs, networking, and building community | Weaknesses – iDigBio has… Non-intuitive website navigation and inconsistent arrangement of resources Minimal data in specimen portal Inconsistent internal communication Insufficient involvement of smaller collections and institutions Insufficient success in promoting diversity and including under-represented groups Lack of explicitly defined of project leadership evaluation plans

## Slide 6: Environmental Scan
 | POSITIVE | NEGATIVE
EXTERNAL | Opportunities – iDigBio should… Highlight research uses of data Develop digitization standards and encourage compliance Advocate for greater digitization funding and formation of cooperative groups across institutions and projects Coordinate efforts across institutions, disciplines, and agencies to bridge initiatives and facilitate networking Integrate directly with collection management software and tools Capture “dark data” from both large and small institutions Collaborate with key existing projects, such as Global Biodiversity Information Facility (GBIF) and Biodiversity Information Serving Our Nation (BISON) | Threats – iDigBio should… Develop a strategy for financial sustainability to reduce dependence on federal funding Develop a strategy for long-term storage and maintenance of its cyberinfrastructure, metadata and images Be mindful of its extremely broad project scope, which includes a vast array of collaborations and partnerships

## Slide 7: Implementation Plan
Affirm project mission, vision, organization, & governance
Define project scope
Define project team, roles, & responsibilities
Identify project milestones, objectives, & strategies
Establish procedures for management of risk, change, quality, & communication

## Slide 8: Project Milestones

## Slide 9: Internal Feedback
Chart: My own roles & responsibilities in iDigBio are clear (n=33)
| Strongly Disagree | Disagree | Neither Agree nor Disagree | Agree | Strongly Agree
FY3 | 0 | 0.07 | 0.28 | 0.41 | 0.24
Chart: I feel I am as informed about project activities, events, decisions, and developments as I need to be given my role in iDigBio (n=33)
| Strongly Disagree | Disagree | Neither Agree nor Disagree | Agree | Strongly Agree
FY3 | 0 | 0.1 | 0.14 | 0.59 | 0.17

## Slide 10: Key iDigBio Accomplishments
Digitization Resources https://www.idigbio.org/wiki/index.php/Digitization_Resources
Workshops and Training https://www.idigbio.org/wiki/index.php/IDigBio_Workshops
Working Groups https://www.idigbio.org/wiki/index.php/IDigBio_Working_Groups
Collaboration & TCN Support https://www.idigbio.org/wiki/index.php/TCN_Resources
Cyberinfrastructure
  Website upgrade www.idigbio.org
  Portal upgrade www.idigbio.org/portal New version just released!
  Data & media ingestion https://www.idigbio.org/wiki/index.php/Data_Ingestion_Report https://www.idigbio.org/portal/publishers

## Slide 11: External Advisory Board Feedback
The EAB was pleased with iDigBio’s progress:
  Valuable service & role as digitization clearinghouse
  iDigBio workshops & symposia highly valued
  Strong focus on digitization & cyberinfrastructure
Recommendations:
  Consider requirements needed for taxonomic hierarchy
  Consider our dual role in organizing geospatial data and the higher value role as a metadata catalog for materials
  Serve iDigBio data to GBIF
iDigBio is currently working to rotate EAB membership

## Slide 12: Overall Community Feedback
What grade would you give iDigBio in moving forward national digitization efforts?
Chart: Community (external; n=101)
| F | D | C | B | A
FY2 | 0 | 0.01 | 0.17 | 0.39 | 0.43
FY3 | 0.01 | 0.01 | 0.07 | 0.55 | 0.36
Chart: iDigBio (internal; n-23)
| F | D | C | B | A
FY2 | 0 | 0 | 0 | 0.8 | 0.2
FY3 | 0 | 0 | 0 | 0.57 | 0.43

## Slide 13: Workshops and Training
 | Total Number of Workshops, Summits, & Symposia | Total Number of Participants | Number of Unique Participants | Number of Unique Institutions
Fiscal Year 1 | 5 | 175 | 128 | 65
Fiscal Year 2 | 12 | 394 | 282 | 160
Fiscal Year 3 | 21 | 702 | 487 | 219
OVERALL | 38 | 1271 | 710 | 309
Chart: 
| FY1 | FY2 | FY3
Total Participants | 175 | 394 | 702
Unique Participants | 128 | 282 | 487

## Slide 14: Workshop Demographics
Chart: Gender
| Female | Male
 | 0.50725 | 0.47246
Chart: Disability
| Hearing | Visual | Mobility | Other | None | Not specified
 | 0.011594 | 0.0028986 | 0.011594 | 0.0028986 | 0.81449 | 0.15362
Chart: Cultural Background
| Hispanic/Latino | Not Hispanic/Latino | Do not wish to provide | Not provided
 | 0.075362 | 0.85217 | 0.028986 | 0.043478
Chart: Ethnicity/Race
| American Indian or Alaskan Native | Asian | African-American or Black | Hawaiian Native or other Pacific Islander | White | Not Provided
 | 0.011594 | 0.04058 | 0.017391 | 0.0057971 | 0.88116 | 0.066667
Chart: Citizenship
| US citizen | Permanent resident | Other non-US citizen | Do not wish to provide | Not provided
 | 0.74783 | 0.06087 | 0.066667 | 0.011594 | 0.11304
Chart: 
| # attendees | # respondents
 | 573 | 345

## Slide 15: Data Ingestion: 15,621,986 Specimen Records

## Slide 16: Data Ingestion: 2,385,568 Media Records

## Slide 17: Community Feedback
Chart: Level of difficulty in submitting data to iDigBio (internal & external; n=52)
| Very Difficult | Difficult | Neutral | Easy | Very Easy
FY3 | 0 | 0.04 | 0.44 | 0.44 | 0.08

## Slide 18: Portal Traffic

## Slide 19: Portal Reach

## Slide 20: Website Traffic

## Slide 21: Website Reach

## Slide 22: Community Feedback
Chart: Overall satisfaction with the iDigBio website (internal & external; n=179)
| Very Dissatisfied | Dissatisfied | Neutral | Satisfied | Very Satisfied
FY3 | 0.01 | 0.03 | 0.38 | 0.51 | 0.07

## Slide 23: Collaboration – Adobe Connect
 | FY1 | FY2 | FY3
Total Users | 40 | 65 | 192
Total Hosts | 12 | 26 | 38
Distinct Meeting Rooms | 37 | 62 | 75
Total Meeting Hours | 768 | 4,429 | 7,522
Total Host Hours | 304 | 2,182 | 2,737
Peak Concurrent Users | 22 | 44 | 102
System Storage Consumption (GB) | 11.4 | 19.2 | 55.7
Meeting Storage Consumption (GB) | 23.9 | 21.7 | 28.4

## Slide 24: Social Media – Facebook

## Slide 25: Social Media – Twitter

## Slide 26: Social Media – Vimeo

## Slide 27: Community Feedback
Chart: Overall satisfaction with iDigBio’s use of social media (internal & external; n=178)
| Very Dissatisfied | Dissatisfied | Neutral | Satisfied | Very Satisfied | I do not engage with iDigBio on social media
FY3 | 0 | 0.02 | 0.27 | 0.24 | 0.09 | 0.38

## Slide 28: Community Feedback
Chart: Overall satisfaction with iDigBio’s newsletter (internal & external; n=140)
| Very Dissatisfied | Dissatisfied | Neutral | Satisfied | Very Satisfied
FY3 | 0 | 0.01 | 0.37 | 0.49 | 0.14