## Slide 1: Business Process Management and Modeling

## Slide 2: Two Key Aspects
Tools for Today: Utilize effective methods to gather information and model workflows
Tools for Ongoing Operations: Review/Refine and maintain effective processes (i.e., continuous workflow improvement)
  Improve Throughput, Cost, Other Key Metrics
  Efficient use of personnel and physical resources (reduce idle time)
  Sufficient redundancy and risk mitigation (risk management at each step)

## Slide 3: Tools for Today
Difficult to draw a workflow diagram as the initial step
Break the activity into manageable chunks
  Modules (various modules for various circumstances; reproducible across disciplines)
  Task Groups
Create a numbered task list (Work Breakdown Structure)
  Contains all tasks for the discrete unit
  Order is initially unimportant (brainstorm)
  Number the tasks within each module or task group (Example: “M1, T1”)
After tasks have been identified, identify dependencies
  List the task number(s) that are dependencies for each task (if applicable)
  Identify the dependency type
    Finish-to-Start (FS): Task B cannot begin until Task A has been completed. This is the most common. Example: “Photograph Specimen” (B) cannot start until “Position Specimen for Imaging” (A) has finished
    Start-to-Finish (SF): Task A must begin before Task B can finish. Extremely rare, and likely not to be utilized in any workflow
    Start-to-Start (SS): Task A must begin before Task B can begin. Example: “Identify Specimens to be Digitized” (A) must begin before “Remove Specimens from the Collection” (B) can begin
    Finish-to-Finish (FF): Task A must finish before Task B can finish. Rare. Example: “Train Workers to Retrieve/Return Specimens” (A) must finish before “Digitized Specimens Returned to the Collection” (B) can finish
Identify resource(s) required for the task – both human resources and physical resources
Identify any required lag times involved between dependent tasks.
  Example: placing a wet herp specimen in a shallow tank (Task A) for imaging (Task C) has a ~30-second lag time (waiting for ripples to diminish before taking the image)
  May also be expressed as a separate task (i.e., Task B = wait for ripples to diminish)
Hint: Tasks that don’t have strict dependencies enable workforce flexibility, feeding the social motivation factors

## Slide 4: Tools for Ongoing Operations
Workflow optimization techniques are numerous, but all have core similarities
  Plan/Design/Document the process
  Measure the process, end-to-end (observation, self-reporting, automated data collection points, log sheets)
  Review the measurements and identify issues (excessive queue times, idle resources)
  Identify opportunities for improvement and implement (include employee input, root causes may be separated from the symptom by several steps)
  Rinse, repeat #2 - #4
Objective, data driven, analytical
Well-documented workflows can seed checklists
Time-centric, but can readily be converted to cost-centric measurements
The duration of a workflow cannot be decreased unless the duration of the Critical Path (your longest chain of dependent events) is decreased
  Break some tasks into smaller units that can run in parallel
  Simplify/automate tasks
  Reassign resources
  Bottlenecks off the Critical Path “don’t matter”
  You will always have a Critical Path

## Slide 5
Plan-Do-Check-Act (Deming Cycle)

## Slide 6
Define
  Write down what you currently know. Seek to clarify facts, set objectives and form the project team. Define the following:
  A problem statement, the customer(s), Critical to Quality (CTQs) — what are the critical process outputs?, the target process and other related business processes, project targets, project boundaries
Measure
  This is the data collection step. The team decides on what should be measured and how to measure it. This forms a data collection plan. It is usual for teams to invest a lot of effort into assessing the suitability of the proposed measurement systems. Good data is at the heart of the DMAIC process:
    Define the process critical Xs (inputs) and Ys (outputs)
    Define the measurement plan
    Test the measurement system
    Collect the data
Analyze
  The data collected in the Measure step is analyzed to determine root causes of defects.
  Identify gaps between current performance and goal performance
  Identify how the process inputs (Xs) affect the process outputs (Ys)
  List and prioritize potential opportunities to improve
  Identify sources of variation
Improve
  Identify creative solutions to fix and prevent process problems
  Create innovate solutions, focus on the simplest and easiest solutions, test solutions, deploy improvements
Control
  Monitor the improvements to ensure continued success, create a control plan, update documents/business process/training records as required.
Tools for Ongoing Operations
Six Sigma DMAIC